## SprintBacklog
Sprint ID/Sprint Name | User Story ID | User Story Description | Task ID | Task Description | Assignee | Estimated Effort (Hours / Story Points) | Actual Effort | Status (To Do / In Progress / Done) | Start Date | End Date | Remarks
Sprint 1 - Foundation & Authentication | US001 | Customer registration with frontend and backend validations | T001 | Create Angular registration reactive form with name, email, phone, username and password validation | a | 6 | 6 | Done | 2026-04-28 | 2026-04-28 | Registration UI and validation completed
Sprint 1 - Foundation & Authentication | US001 | Customer registration with frontend and backend validations | T002 | Implement Spring Boot register API, duplicate checks and password hashing | b | 7 | 7 | Done | 2026-04-28 | 2026-04-29 | Backend registration service completed
Sprint 1 - Foundation & Authentication | US001 | Customer registration with frontend and backend validations | T003 | Create customer acknowledgement response and frontend success flow | c | 4 | 4 | Done | 2026-04-29 | 2026-04-29 | Registration confirmation added
Sprint 1 - Foundation & Authentication | US002 | Role based login and forgot password | T004 | Implement login form for customer admin and staff roles | d | 5 | 5 | Done | 2026-04-28 | 2026-04-29 | Role selector and login popup added
Sprint 1 - Foundation & Authentication | US002 | Role based login and forgot password | T005 | Implement backend login validation and account lockout handling | e | 6 | 6 | Done | 2026-04-29 | 2026-04-30 | Failed attempts and locked account checks added
Sprint 1 - Foundation & Authentication | US002 | Role based login and forgot password | T006 | Replace OTP reset flow with username email and phone verification | f | 6 | 7 | Done | 2026-05-12 | 2026-05-13 | Feedback change completed after review
Sprint 1 - Foundation & Authentication | US003 | Homepage and authenticated navigation | T007 | Build landing page room card navigation and public navbar | g | 5 | 5 | Done | 2026-04-29 | 2026-04-30 | Landing room cards prepared
Sprint 1 - Foundation & Authentication | US003 | Homepage and authenticated navigation | T008 | Remove public Home Login Register links from admin and staff after login | h | 4 | 4 | Done | 2026-05-11 | 2026-05-11 | Feedback UI cleanup completed
Sprint 1 - Foundation & Authentication | US013 | Profile edit flow | T009 | Create read-only customer profile with Edit Save and Cancel flow | i | 6 | 6 | Done | 2026-04-30 | 2026-05-01 | Customer profile flow completed
Sprint 1 - Foundation & Authentication | US013 | Profile edit flow | T010 | Add admin and staff profile sections using same form behavior | j | 6 | 6 | Done | 2026-05-06 | 2026-05-07 | Admin and staff profiles added
Sprint 2 - Customer Booking & Payments | US004 | Search room availability | T011 | Create customer room search filters for city hotel room type date and amenities | a | 7 | 7 | Done | 2026-05-01 | 2026-05-04 | Search filters implemented
Sprint 2 - Customer Booking & Payments | US004 | Search room availability | T012 | Implement customer room availability APIs and room response mapping | b | 8 | 8 | Done | 2026-05-01 | 2026-05-04 | Search API completed
Sprint 2 - Customer Booking & Payments | US005 | Customer room booking confirmation | T013 | Build booking confirmation screen with calculated nights room count GST and total | c | 8 | 8 | Done | 2026-05-04 | 2026-05-05 | Booking confirmation completed
Sprint 2 - Customer Booking & Payments | US005 | Customer room booking confirmation | T014 | Add guest limit validation and popup for more than 12 guests | d | 3 | 4 | Done | 2026-05-13 | 2026-05-13 | Bug fix completed from feedback
Sprint 2 - Customer Booking & Payments | US005 | Customer room booking confirmation | T015 | Preserve selected landing room details into booking flow | e | 4 | 4 | Done | 2026-05-05 | 2026-05-05 | Landing Book Now flow connected
Sprint 2 - Customer Booking & Payments | US006 | Payment form and timer | T016 | Create card payment form with card number CVV expiry and cardholder validation | f | 6 | 6 | Done | 2026-05-05 | 2026-05-06 | Payment validation completed
Sprint 2 - Customer Booking & Payments | US006 | Payment form and timer | T017 | Implement 5 minute payment timer and stale payment prevention | g | 5 | 5 | Done | 2026-05-06 | 2026-05-06 | Timer completed
Sprint 2 - Customer Booking & Payments | US006 | Payment form and timer | T018 | Implement booking creation and bill creation on payment success | h | 7 | 7 | Done | 2026-05-05 | 2026-05-06 | Booking payment persistence completed
Sprint 2 - Customer Booking & Payments | US007 | PDF invoice receipt | T019 | Generate PDF receipt with booking transaction user room dates amount and tax | i | 7 | 7 | Done | 2026-05-06 | 2026-05-07 | OpenPDF receipt generation completed
Sprint 2 - Customer Booking & Payments | US007 | PDF invoice receipt | T020 | Add customer and admin receipt download actions | j | 4 | 4 | Done | 2026-05-07 | 2026-05-07 | Receipt download added
Sprint 2 - Customer Booking & Payments | US008 | Booking history | T021 | Split My Bookings into upcoming and past booking sections | a | 5 | 5 | Done | 2026-05-07 | 2026-05-07 | Booking sections completed
Sprint 2 - Customer Booking & Payments | US008 | Booking history | T022 | Add arrow pagination to upcoming and past bookings | b | 4 | 4 | Done | 2026-05-11 | 2026-05-11 | Feedback pagination style applied
Sprint 2 - Customer Booking & Payments | US009 | Update reservation | T023 | Create modify booking form and recalculate dates guests taxes and totals | c | 7 | 7 | Done | 2026-05-07 | 2026-05-08 | Customer modify flow completed
Sprint 2 - Customer Booking & Payments | US010 | Cancel booking | T024 | Add cancellation confirmation popup and cancel API update | d | 5 | 5 | Done | 2026-05-08 | 2026-05-08 | Cancellation modal completed
Sprint 3 - Admin Staff Complaints & Stabilization | US011 | Register complaint | T025 | Create complaint form with booking category title description and contact validation | e | 6 | 6 | Done | 2026-05-04 | 2026-05-05 | Complaint form completed
Sprint 3 - Admin Staff Complaints & Stabilization | US011 | Register complaint | T026 | Add backend complaint eligibility ownership and one week checkout validation | f | 7 | 7 | Done | 2026-05-05 | 2026-05-06 | Complaint rules completed
Sprint 3 - Admin Staff Complaints & Stabilization | US012 | Track complaint status | T027 | Create View Complaints section with status and response display | g | 5 | 5 | Done | 2026-05-06 | 2026-05-06 | Complaint tracking completed
Sprint 3 - Admin Staff Complaints & Stabilization | US012 | Track complaint status | T028 | Add pagination to customer View Complaints | h | 3 | 3 | Done | 2026-05-11 | 2026-05-11 | Feedback pagination completed
Sprint 3 - Admin Staff Complaints & Stabilization | US014 | Admin dashboard | T029 | Create admin dashboard sections and authenticated admin navigation | i | 6 | 6 | Done | 2026-05-01 | 2026-05-04 | Admin shell completed
Sprint 3 - Admin Staff Complaints & Stabilization | US015 | Manage rooms | T030 | Build room listing search edit flow and arrow pagination | j | 7 | 7 | Done | 2026-05-04 | 2026-05-05 | Room listing completed
Sprint 3 - Admin Staff Complaints & Stabilization | US016 | Add rooms | T031 | Create add room form and backend save room API | a | 6 | 6 | Done | 2026-05-05 | 2026-05-06 | Room add completed
Sprint 3 - Admin Staff Complaints & Stabilization | US017 | Manage reservations | T032 | Create admin all reservations listing with pagination | b | 6 | 6 | Done | 2026-05-06 | 2026-05-07 | Reservation listing completed
Sprint 3 - Admin Staff Complaints & Stabilization | US017 | Manage reservations | T033 | Add admin booking modification with dynamic total recalculation | c | 7 | 7 | Done | 2026-05-07 | 2026-05-08 | Admin modify booking completed
Sprint 3 - Admin Staff Complaints & Stabilization | US018 | Search reservations | T034 | Add reservation filters for date user room status and payment status | d | 5 | 5 | Done | 2026-05-07 | 2026-05-08 | Reservation filters completed
Sprint 3 - Admin Staff Complaints & Stabilization | US019 | Manage customer accounts | T035 | Create customer accounts listing and pagination | e | 5 | 5 | Done | 2026-05-06 | 2026-05-07 | Customer accounts completed
Sprint 3 - Admin Staff Complaints & Stabilization | US020 | Search bills | T036 | Create Search Bills section with pagination | f | 4 | 4 | Done | 2026-05-07 | 2026-05-08 | Bills pagination completed
Sprint 3 - Admin Staff Complaints & Stabilization | US021 | Manage bills | T037 | Wire bill listing and receipt download integration | g | 5 | 5 | Done | 2026-05-08 | 2026-05-08 | Bills integration completed
Sprint 3 - Admin Staff Complaints & Stabilization | US022 | Manage complaints admin | T038 | Create admin complaint dashboard with pagination and filters | h | 6 | 6 | Done | 2026-05-06 | 2026-05-07 | Admin complaint dashboard completed
Sprint 3 - Admin Staff Complaints & Stabilization | US022 | Manage complaints admin | T039 | Implement complaint assignment workflow and audit timestamps | i | 7 | 7 | Done | 2026-05-07 | 2026-05-08 | Assignment workflow completed
Sprint 3 - Admin Staff Complaints & Stabilization | US023 | Manage complaints staff | T040 | Create staff complaint workspace and status update form | j | 6 | 6 | Done | 2026-05-05 | 2026-05-06 | Staff workspace completed
Sprint 3 - Admin Staff Complaints & Stabilization | US023 | Manage complaints staff | T041 | Add staff complaint pagination and profile section | a | 5 | 5 | Done | 2026-05-11 | 2026-05-11 | Feedback pagination and profile completed
Sprint 4 - Feedback Bugs & Final Polish | US002 | Login popup and modal fixes | T042 | Ensure login confirmation popup blocks background scrolling and interaction | b | 3 | 3 | Done | 2026-05-12 | 2026-05-12 | Feedback bug fixed
Sprint 4 - Feedback Bugs & Final Polish | US003 | UI style feedback | T043 | Remove border radius across project and replace gradient buttons with light blue buttons | c | 5 | 5 | Done | 2026-05-12 | 2026-05-12 | Manager feedback applied
Sprint 4 - Feedback Bugs & Final Polish | US015 | Pagination style feedback | T044 | Replace numbered pagination with simple previous next arrows across admin customer and staff tables | d | 5 | 5 | Done | 2026-05-11 | 2026-05-12 | Pagination simplified
Sprint 4 - Feedback Bugs & Final Polish | US014 | Profile navbar feedback | T045 | Remove profile circle and keep only View Profile button in admin and staff navbar | e | 3 | 3 | Done | 2026-05-12 | 2026-05-12 | Navbar feedback completed
Sprint 4 - Feedback Bugs & Final Polish | US006 | Payment validation feedback | T046 | Finalize immediate card number CVV expiry and cardholder frontend validations | f | 4 | 4 | Done | 2026-05-11 | 2026-05-12 | Payment validation feedback completed
Sprint 4 - Feedback Bugs & Final Polish | US013 | Profile validation feedback | T047 | Verify frontend validations on profile forms for customer admin and staff | g | 4 | 4 | Done | 2026-05-12 | 2026-05-13 | Profile validation verified
Sprint 4 - Feedback Bugs & Final Polish | US022 | Complaint status feedback | T048 | Verify admin and staff complaint status persistence and popup confirmations | h | 4 | 4 | Done | 2026-05-12 | 2026-05-13 | Complaint update feedback completed
Sprint 4 - Feedback Bugs & Final Polish | US008 | Final build verification | T049 | Run frontend build and backend package verification | i | 3 | 3 | Done | 2026-05-13 | 2026-05-13 | Builds passed with warnings only
Sprint 4 - Feedback Bugs & Final Polish | US007 | Documentation support | T050 | Prepare user manual and code documentation deliverables | j | 5 | 5 | Done | 2026-05-13 | 2026-05-13 | Final deliverables prepared

## BurnDownChart
BurnDownChart - Sprint Progress Visualization
Data source: SprintBacklog sheet. Weekends are excluded. Core sprint execution runs 28-Apr-2026 to 08-May-2026; bugs and feedback updates continue through 13-May-2026.
Sprint Day | Ideal Remaining Effort | Actual Remaining Effort | Completed Actual Effort | Total Estimated Effort | 267
2026-04-28 | 267 | 263 | 6 | Total Actual Effort | 269
2026-04-29 | 242.73 | 247 | 22 | Assignees | a, b, c, d, e, f, g, h, i, j
2026-04-30 | 218.45 | 236 | 33 | Weekend Exclusion | 02-May, 03-May, 09-May, 10-May excluded
2026-05-01 | 194.18 | 230 | 39
2026-05-04 | 169.91 | 209 | 60
2026-05-05 | 145.64 | 184 | 85
2026-05-06 | 121.36 | 142 | 127 | Assignee | Estimated Effort | Actual Effort
2026-05-07 | 97.09 | 103 | 166 | a | 29 | 29
2026-05-08 | 72.82 | 63 | 206 | b | 28 | 28
2026-05-11 | 48.55 | 47 | 222 | c | 31 | 31
2026-05-12 | 24.27 | 27 | 242 | d | 23 | 24
2026-05-13 | 0 | 0 | 269 | e | 24 | 24
|  |  |  | f | 27 | 28
|  |  |  | g | 24 | 24
|  |  |  | h | 24 | 24
|  |  |  | i | 29 | 29
|  |  |  | j | 28 | 28